## Lead
Project Name: First Cry Group Number - 1 Team Lead- Anupam Mishra

## Status Meeting Group
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2024-03-18 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-19 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-20 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-21 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-22 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-23 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-24 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓
2024-03-25 | 9:30 |  | 2:30 |  | 5:30
2024-03-26 | 9:30 | ✓ | 2:30 | ✓ | 5:30 | ✓

## Project Status Check
Sl.no | Employee ID | Name | Domain | Module | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26
1 | 2587363 | Anupam Mishra | Testing | Preschool Locator | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
2 | 2586991 | Gurijala SaiChandu | Testing | Add to Cart | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
3 | 2587014 | Kaliga VinayKumar | Testing | My Profile | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
4 | 2587024 | Kokkanti Lokesh | Testing | Login | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
5 | 2587017 | Meegada Sunitha | Testing | Cart | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
6 | 2586652 | Nandeesh N | Testing | Find Stores | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
7 | 2587325 | Rapaka Hiranmai | Testing | Search | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation
8 | 2586685 | Thamatam Chandana | Testing | ShortList | Test Design - Design | Automation Script - Pages | Automation Script - Test | Automation Script - Utilities | Assertions | Reporting | Hybrid Framework |  | Resolve the defects | Presentation